Instructions for Submission of Project Data and Other Communications for the Large Load Interconnection Process

Version 1.0

Document Revisions

| Date | Version | Description | Author(s) |
| --- | --- | --- | --- |
| 12/15/2025 | 1.0 | Initial Release | ERCOT Staff |
| 02/12/2026 | 1.1 | Clarification of documentation required under PG 9.5.1(1)(a)(i) and 9.5.2(1)(a)(i) | ERCOT Staff |

Table of Contents

1.	Document Overview	1

2.	Instructions for Submission of Information	1

3.	Explanation of ERCOT Communications	4

Document Overview

Pursuant to Planning Guide Section 9.1(2), ERCOT is required to publicly post the manner and format for submitting all project information and other communications related to the Large Load Interconnection process. This document is posted to meet this requirement. Questions on this form should be emailed to LargeLoadInterconnection@ercot.com.

Instructions for Submission of Information

The manner and format for submission of required information and communications described in Section 9 of the ERCOT Planning Guide is detailed in the table below.

| Topic | Instructions for Submission | Planning Guide Reference(s) |
| --- | --- | --- |
| Request access to the TSP confidential distribution list (Transmission Owner Load Interconnection) | To subscribe to the Large Loads distribution list, go to lists.ercot.com. If you do not currently subscribe to any lists, you will need to create an account. If you have an account, log in. To create an account: Click Log In and select Register Password to create an account. Follow the steps on the screen. You will need to confirm your email before the password is registered. It will sometimes go to “other” or junk mail. Check these folders if you do not receive an email. If you have an existing account: Click Log In and enter your password. Under Subscribe, search for Large_Loads. Enter your name in the Name field. Hit the Subscribe button. You will need to be approved since this is a private list. | 9.1(3) |
| Initial submission of Large Load project information and Load Commissioning Plan (LCP) | The TSP must submit a copy of the Load Information Form (LIF) with all indicated fields completed on the LIF tab and the LCP tab to LargeLoadInterconnection@ercot.com. This form is available on the Large Load Integration section of the ERCOT website. | 9.2.2(1)(a), (b) |
| Submission of written acknowledgement from the Interconnecting Large Load Entity (ILLE) to abide by Planning Guide Section 9.2.3 | The TSP must send a copy of this written acknowledgement to LargeLoadInterconnection@ercot.com. This may be included as an attachment with the submission of the initial LIF and does not need to be a separate email. | 9.2.2(1)(c), 9.2.3 |
| Submission of a formal request to initiate the Large Load Interconnection Study (LLIS) process | The TSP may - Include text requesting to initiate the LLIS process in the body of the email containing the initial LIF; OR - Submit a separate email with this request to LargeLoadInterconnection@ercot.com. | 9.2.2(1)(d) |
| Submit payment of the LLIS Application Fee | This language is currently not effective. This document will be updated with instructions when the language is implemented. | 9.2.2(1)(e), (3) |
| Update Large Load project information when a material change occurs. | The TSP must take the most current Load Information Form submitted to ERCOT, update all fields on the LIF tab affected by the change, and update the date current field. The updated form must then be submitted to LargeLoadInterconnection@ercot.com. This may be done simultaneously with an LCP update (see below). IF the updated information differs substantially from the dynamic model information used in the LLIS Stability Study, the TSP must also include a written statement in the body of the email submission detailing whether it believes a new Stability Study is required and the basis for that determination. | 9.2.3(1), (2) |
| Update the LCP with new information. | The TSP must take the most current Load Information Form submitted to ERCOT, update all fields on the LCP tab affected by the change, and update the date current field. The updated form must then be submitted to LargeLoadInterconnection@ercot.com. This may be done simultaneously with an LIF update (see above). As a reminder, an LCP update is required on the conclusion of the LLIS as described in Section 9.4, and upon execution of all agreements as described in Section 9.5. It is also required in the event a material change impacting the project timeline occurs. Finally, the TSP is obligated to maintain the LCP until the project reaches its full requested level of peak Demand. | 9.2.4, 9.4, 9.5 |
| Request to participate in an LLIS as an affected TSP. | Send an email to both the identified lead TSP contact from the ERCOT notification and LargeLoadInterconnection@ercot.com stating the request. The email must reference the LLI number and include one or more contacts for the project. | 9.3.2(2) |
| Scheduling a LLIS Kickoff Meeting | The lead TSP will send an invite to the associated ERCOT engineer (if assigned) and LargeLoadInterconnection@ercot.com, as well as to contacts for all affected TSPs. The lead TSP should consult with all parties before sending an invite to identify available times. | 9.3.2(3) |
| Submission of a preliminary or final LLIS Study Scope | The lead TSP must send the study scope document to the associated ERCOT engineer, LargeLoadInterconnection@ercot.com, and to contacts for all affected TSPs. | 9.2.3(6), (8) |
| Submission of comments on a preliminary LLIS Study Scope | ERCOT and any affected TSPs must provide all comments in writing by email sent to the submitter of the study scope. | 9.2.3(7) |
| Submission of a preliminary or final LLIS report | The lead TSP must send the study report document to the associated ERCOT engineer, LargeLoadInterconnection@ercot.com, and to contacts for all affected TSPs. | 9.4(1), (5) |
| Submission of comments on a preliminary LLIS report | ERCOT and any affected TSPs must provide all comments in writing by email sent to the submitter of the study report. | 9.4(2) |
| Request an extension to complete agreements with the ILLE | The TSP may request an extension to complete agreements and provide an opinion on the need for LLIS restudy within 30 days of receiving a notice from ERCOT by replying to the email. | 9.4(9) |
| Provide an opinion on the need for study updates for loads that have not energized within 1 year of studied in-service date | The lead TSP should provide its opinion to ERCOT in writing by emailing the assigned ERCOT engineer and LargeLoadInterconnection@ercot.com. | 9.4(10) |
| Confirmation that all required interconnection agreements have been signed with the ILLE, Interconnecting Entity (IE), and/or Resource Entity (RE), if applicable | The interconnecting TSP must send the confirmation email to LargeLoadInterconnection@ercot.com. This email may also include other items prescribed in Section 9.5. If the required agreements include a SGIA, the SGIA must be provided as a change request in RIOO-RS. ERCOT may request to see copies of the executed interconnection agreement(s) and other necessary agreements described in 9.5.1(1)(a)(i) and 9.5.2(1)(a)(i). The interconnecting TSP must provide these on request. | 9.5.1(1)(a)(i) 9.5.2(1)(a)(i) |
| Confirmation of ILLE acknowledgement of obligations | The interconnecting TSP must send an email to LargeLoadInterconnection@ercot.com. This email must include the date the acknowledgement from the ILLE (or RE, if applicable) was received. This email does not need to be separate. It can be combined with other notifications prescribed in Section 9.5. | 9.5.1(1)(a)(ii) 9.5.2(1)(a)(ii) |
| Confirmation that the interconnecting TSP has received notice to proceed | The interconnecting TSP must send an email to LargeLoadInterconnection@ercot.com. This email must include the date the notice to proceed was received. This email does not need to be separate. It can be combined with other notifications prescribed in Section 9.5. | 9.5.1(1)(a)(iii) 9.5.2(1)(a)(iii) |
| Confirmation that the interconnecting TSP has received all required financial security from the ILLE | The interconnecting TSP must send an email to LargeLoadInterconnection@ercot.com. This email must include the date the last portion of the required security was received. This email does not need to be separate. It can be combined with other notifications prescribed in Section 9.5. | 9.5.1(1)(a)(iv) 9.5.2(1)(a)(iv) |
| Submission of the SSO study report and explanation of SSO countermeasures, monitoring, and mitigation plans | The lead TSP must send the study report and any additional documents to the associated ERCOT engineer, LargeLoadInterconnection@ercot.com, jonathan.rose@ercot.com, and sunwook.kang@ercot.com. | 9.6(1)(d) |
| Request to Energize a new Large Load not netted with a Generation Resource or ESR | The interconnecting TSP should complete and ERCOT must approve the Energization Request for New Standalone Large Load form posted on Large Load Integration section of the ERCOT website. The TSP must attach an up to date LCP or include a statement with the email that the most recently submitted LCP remains accurate. | 9.6(1) |
| Request to Energize a new Large Load netted with a Generation Resource or ESR | The Resource Entity for the netted load must complete and ERCOT must approve New Generator Commissioning Checklist Part 1 available on the Resource Integration section of the ERCOT website. The RE must attach an up to date LCP or include a statement with the email that the most recently submitted LCP remains accurate. | 9.6(1) |
| Notification of a Large Load exceeding a limit on Demand established in the LCP. | If identified, the TSP should email LargeLoadInterconnection@ercot.com. | 9.6(2)(a) |
| Request to increase the level of approved peak Demand for a Large Load after one or more transmission upgrades identified in the LCP becomes operational | The interconnecting TSP must email LargeLoadInterconnection@ercot.com stating which upgrade(s) has become operational and indicate the level of demand in the LCP for the Large Load is being requested. ERCOT must approve this request in writing. ERCOT is preparing a form to handle these requests and will update this document once this form is available. | 9.6(2)(b) |
| Provision of new or updated Large Load dynamic models to ERCOT | Email LargeLoadInterconnection@ercot.com with the model as an attachment. Clearly indicate the LLI number associated with the dynamic model. | 9.6(2)(c) |

Explanation of ERCOT Communications

The manner and format for communications originating from ERCOT to the TSP, RE, and/or ILLE are detailed below.

| Topic | Explanation of ERCOT Communication | Planning Guide Reference(s) |
| --- | --- | --- |
| Communication of the LLIS number for a new request. | ERCOT will respond to the initial email submission sent to LargeLoadInterconnection@ercot.com. The email may be sent from the Large Load inbox or by an individual ERCOT engineer. |  |
| Notification of a complete LLI submission. | ERCOT will respond to the initial email submission sent to LargeLoadInterconnection@ercot.com. The email may be sent from the Large Load inbox or by an individual ERCOT engineer. | 9.3.2(1) |
| Notification to TSPs of a new LLIS request. | ERCOT will send an email to the TSP confidential distribution list (Transmission Owner Load Interconnection) with the LLI number, identity of the interconnecting TSP, the lead TSP (if different, and other relevant information about the project. | 9.3.2(1), 9.1(3) |
| Comments on a final LLIS Study Scope | ERCOT will provide all comments in writing by email sent to the submitter of the study scope. | 9.2.3(9) |
| Notification of extension of the review period for a LLIS study report | ERCOT will email the submitter of the LLIS study report and contacts for all affected TSPs with the notification that it has extended the review period by 20 Business Days as provided in Planning Guide Section 9.4(2). | 9.4(2) |
| Communication of final results of a LLIS | ERCOT will provide notification of the finalization of the LLIS and all information required by Planning Guide Section 9.4(6) by email to contacts for the lead TSP and affected TSPs. | 9.4(6) |
| Request for study update or restudy after a material change to project information | After receiving an updated LIF and/or LCP under the conditions defined in Planning Guide Section 9, ERCOT will notify the contact for the lead TSP by email if one or more LLIS study assumptions are impacted. ERCOT and the TSP will collaborate by email on whether a restudy is required. ERCOT and the TSP may have one or more meetings if needed. However, the final determination will be communicated through email. | 9.4(8) |
| Notification to the lead TSP of failure to meet requirements of PG 9.5 after 180 days. | ERCOT will send an email to the lead TSP contact for the project under the conditions described in Planning Guide 9.4(9). The TSP may request an extension to complete agreements and provide an opinion on the need for LLIS restudy by replying to this email within 30 days. | 9.4(9) |
| Notification of LLI project cancellation | ERCOT will send an email to the lead TSP contact for the project under the conditions described in Planning Guide 9.4(9). | 9.4(9) |
| Notice of failure to energize within 1 year of studied in-service date | Though not required by the Planning Guide, ERCOT will send a courtesy notice to the lead TSP. | 9.4(10) |
| Approval of request to energize a new standalone Large Load | ERCOT will issue approval via email sent to the TSP that submitted the Energization Request for New Standalone Large Load form. | 9.6(1) |
| Approval of request to energize a new netted Large Load | ERCOT will issue approval via email sent to the RE New Generator Commissioning Checklist Part 1. The TSP will be cc’d. | 9.1(6) |
| Approval to increase the level of approved peak Demand for a Large Load after one or more transmission upgrades identified in the LCP becomes operational | ERCOT will issue approval via email. | 9.6(2)(b) |